## Use Case List
ShiftSmart – Mobile Workforce Management System
# | Use Case ID | Module | Use Case Name | Description / User Story | Acceptance Criteria | Actor | Priority | Status
Complete Use Case Register ¦ Roles: Employee · Manager · Super Admin
AUTHENTICATION
1 | UC-C01 | AUTHENTICATION | Login to the App | As a user I want to log in using my email and password so that I can access the mobile application. | • Email & password fields present • Successful login redirects by role • Error shown for wrong credentials | Employee / Manager / Admin | High | Planned
2 | UC-C02 | AUTHENTICATION | Automatic Session Check | As a user I want the app to check my previous login session so that I do not need to log in again every time. | • Token/session checked on app launch • Redirects to correct dashboard if valid • Shows login screen if expired | Employee / Manager / Admin | High | Planned
3 | UC-C03 | AUTHENTICATION | Biometric Login | As a user I want to use Face ID or fingerprint login so that I can sign in quickly and securely. | • Biometric prompt appears on supported devices • Uses saved credentials • Fallback to password available | Employee / Manager / Admin | High | Planned
4 | UC-C04 | AUTHENTICATION | Enable Biometric Login | As a user I want to enable biometric login after signing in so that future logins are easier. | • App asks permission before saving biometric preference • Preference stored in shared preferences | Employee / Manager / Admin | Medium | Planned
5 | UC-C05 | AUTHENTICATION | Disable Biometric Login | As a user I want to disable biometric login so that my account requires password login again. | • Option available in settings • Biometric preference cleared | Employee / Manager / Admin | Medium | Planned
6 | UC-C06 | AUTHENTICATION | Forgot Password | As a user I want to reset my password so that I can recover access if I forget it. | • Password reset option visible on login screen • Reset email/OTP sent successfully | Employee / Manager / Admin | High | Planned
7 | UC-C07 | AUTHENTICATION | Verify Password Reset OTP | As a user I want to enter an OTP code so that the system can confirm my password reset request. | • OTP entry screen shown • Invalid OTP shows error • Valid OTP proceeds to new password screen | Employee / Manager / Admin | High | Planned
8 | UC-C08 | AUTHENTICATION | Create New Password | As a user I want to create a new password so that I can log in again after resetting my account. | • New password and confirm password fields present • Password updated successfully | Employee / Manager / Admin | High | Planned
9 | UC-C09 | AUTHENTICATION | Change Password | As a user I want to change my password from settings so that I can keep my account secure. | • Old and new password fields present • Password updated successfully | Employee / Manager / Admin | Medium | Planned
10 | UC-C10 | AUTHENTICATION | Logout | As a user I want to log out so that my account is not accessible from the device. | • Session cleared on logout • Biometric preference preserved • Returns to login screen | Employee / Manager / Admin | High | Planned
11 | UC-C11 | AUTHENTICATION | Role-Based Redirect | As a logged-in user I want to be redirected to the correct dashboard based on my role. | • Employee → Employee dashboard • Manager/Admin → Manager dashboard | Employee / Manager / Admin | High | Planned
PROFILE & SETTINGS
12 | UC-P01 | PROFILE & SETTINGS | View Own Profile | As a user I want to view my profile so that I can confirm my personal information. | • Profile screen accessible from nav • All fields displayed correctly | Employee / Manager / Admin | High | Planned
13 | UC-P02 | PROFILE & SETTINGS | Update Own Profile | As a user I want to update my profile details so that my information stays correct. | • Name, contact, address, and other fields editable • Changes saved successfully | Employee / Manager / Admin | High | Planned
14 | UC-P03 | PROFILE & SETTINGS | Upload Profile Image | As a user I want to upload a profile image so that other users can identify me easily. | • Camera / gallery picker available • Avatar updated and visible | Employee / Manager / Admin | Medium | Planned
15 | UC-P04 | PROFILE & SETTINGS | View Profile Header in Side Menu | As a user I want to see my profile summary in the side menu so that I know which account is active. | • Profile header shows name, role, and avatar | Employee / Manager / Admin | Medium | Planned
16 | UC-P05 | PROFILE & SETTINGS | Refresh Profile from Backend | As a user I want my profile to refresh from the backend so that the app shows the latest information. | • Profile refreshed on side nav open | Employee / Manager / Admin | Medium | Planned
17 | UC-P06 | PROFILE & SETTINGS | Open Settings | As a user I want to open settings so that I can manage my account and app preferences. | • Settings screen accessible from side menu • Changes saved | Employee / Manager / Admin | Medium | Planned
NOTIFICATIONS
18 | UC-N01 | NOTIFICATIONS | Receive Push Notifications | As a user I want to receive push notifications so that I am informed even when the app is closed. | • FCM token registered on login • APNs token registered on iOS • Background message handler active | Employee / Manager / Admin | High | Planned
19 | UC-N02 | NOTIFICATIONS | View Notifications | As a user I want to view notifications so that I can see important updates in one place. | • Unread and read notifications listed • Notifications screen accessible from nav | Employee / Manager / Admin | High | Planned
20 | UC-N03 | NOTIFICATIONS | Mark Notification as Read | As a user I want to mark notifications as read so that I can separate new updates from old ones. | • Mark-as-read action updates status • Notification list refreshes | Employee / Manager / Admin | Medium | Planned
21 | UC-N04 | NOTIFICATIONS | Open Notification Details | As a user I want to tap a notification and open the related screen so that I can act quickly. | • Notification payload routes to correct screen | Employee / Manager / Admin | High | Planned
22 | UC-N05 | NOTIFICATIONS | Receive Emergency Alert (Manager) | As a manager I want to receive emergency alerts from employees so that I can respond quickly. | • Emergency clock-out triggers manager notification | Manager / Admin | High | Planned
23 | UC-N06 | NOTIFICATIONS | Receive Leave Decision Notification | As an employee I want to receive a notification when my leave is approved or rejected. | • Push notification sent on leave status update | Employee | High | Planned
24 | UC-N07 | NOTIFICATIONS | Receive Shift Notification | As an employee I want to receive a notification when assigned to a shift. | • Push notification sent on shift assignment | Employee | High | Planned
25 | UC-N08 | NOTIFICATIONS | Shift Completion Notification to Manager | As an employee I want my manager to be notified when I complete a shift. | • Notification sent to manager on shift completion | Employee | Medium | Planned
26 | UC-N09 | NOTIFICATIONS | Send Leave Request Notification to Manager | As an employee I want my manager to receive a notification when I submit a leave request. | • Notification sent to manager on leave submission | Employee | High | Planned
CHAT
27 | UC-CH01 | CHAT | View Chat List | As a user I want to view my chat conversations so that I can continue communication. | • Chat list fetched and displayed | Employee / Manager | High | Planned
28 | UC-CH02 | CHAT | Search User for Chat | As a user I want to search for another user so that I can start a new conversation. | • Search returns matching employees/managers | Employee / Manager | Medium | Planned
29 | UC-CH03 | CHAT | Create New Chat | As a user I want to create a new chat so that I can message someone I have not chatted with before. | • New chat created and opens chat box | Employee / Manager | Medium | Planned
30 | UC-CH04 | CHAT | Send Chat Message | As a user I want to send messages so that I can discuss work updates. | • Message delivered and visible to recipient • Chat history preserved | Employee / Manager | High | Planned
31 | UC-CH05 | CHAT | View Chat History | As a user I want to view old messages so that I can understand past conversations. | • Messages fetched by participant ID | Employee / Manager | High | Planned
FILES & MEDIA
32 | UC-F01 | FILES & MEDIA | Upload File | As a user I want to upload files so that I can attach documents when required. | • File picker opens • File uploaded successfully via multipart API | Employee / Manager | High | Planned
33 | UC-F02 | FILES & MEDIA | Preview Uploaded Media | As a user I want to preview uploaded images or files so that I know I selected the correct document. | • Media viewer screen shows image/file preview | Employee / Manager | Medium | Planned
34 | UC-F03 | FILES & MEDIA | Open Uploaded Document | As a user I want to open a document so that I can check what I submitted. | • Document opens in media viewer | Employee / Manager | Low | Planned
SYSTEM / UX
35 | UC-SY01 | SYSTEM / UX | Use App on Different Screen Sizes | As a user I want the app layout to work on different mobile devices so that I can use it comfortably. | • Responsive utilities applied • No overflow or clipping on any device | Employee / Manager / Admin | Medium | Planned
36 | UC-SY02 | SYSTEM / UX | View Restricted Feature Message | As a user I want to see a clear message when a feature is restricted so that I understand why I cannot access it. | • FeatureGate widget shows restriction message | Employee / Manager | Medium | Planned
37 | UC-SY03 | SYSTEM / UX | Validate Required Form Fields | As a user I want forms to validate required fields so that I do not submit incomplete information. | • Validation error shown on empty required fields | Employee / Manager / Admin | High | Planned
38 | UC-SY04 | SYSTEM / UX | Pick Dates from Date Picker | As a user I want to select dates using a date picker so that I avoid typing date values manually. | • Date picker widget opens and returns selected date | Employee / Manager | High | Planned
39 | UC-SY05 | SYSTEM / UX | Pick Time for Shift | As a manager I want to select shift times using a time input so that scheduling is accurate. | • Time widget opens and returns selected time | Manager | High | Planned
40 | UC-SY06 | SYSTEM / UX | Use Dark Map Style | As a user I want the map to match the app's dark theme so that the visual experience is consistent. | • Dark map style (dark.json) applied | Employee / Manager | Low | Planned
41 | UC-SY07 | SYSTEM / UX | FAQ | As a user I want to read FAQ information so that I can understand app usage and company processes. | • FAQ section accessible • Questions and answers clearly displayed | Employee / Manager | Low | Planned
EMPLOYEE – DASHBOARD & SHIFTS
42 | UC-E01 | EMPLOYEE – DASHBOARD & SHIFTS | View Employee Dashboard | As an employee I want to view my dashboard so that I can quickly access my work information. | • Bottom nav: Home, Shifts, Chat, Leave • Today's shift visible on home | Employee | High | Planned
43 | UC-E02 | EMPLOYEE – DASHBOARD & SHIFTS | View Assigned Shifts | As an employee I want to view my assigned shifts so that I know when I need to work. | • Shift list with date, time, site, job shown • Past and upcoming shifts separated | Employee | High | Planned
44 | UC-E03 | EMPLOYEE – DASHBOARD & SHIFTS | View Shift Details | As an employee I want to open a shift so that I can see full details like time, site, job, and status. | • Job, site, time, status visible | Employee | High | Planned
45 | UC-E04 | EMPLOYEE – DASHBOARD & SHIFTS | Accept Shift | As an employee I want to accept a shift so that my manager knows I am available. | • Accept action saved • Manager notified | Employee | High | Planned
46 | UC-E05 | EMPLOYEE – DASHBOARD & SHIFTS | Reject Shift | As an employee I want to reject a shift so that my manager knows I cannot attend. | • Reject action saved • Manager notified for reassignment | Employee | High | Planned
47 | UC-E06 | EMPLOYEE – DASHBOARD & SHIFTS | Request Shift Swap | As an employee I want to request a shift swap so that another employee may cover my shift. | • Swap request submitted • Manager receives notification | Employee | Medium | Planned
48 | UC-E07 | EMPLOYEE – DASHBOARD & SHIFTS | View Job Linked to Shift | As an employee I want to view the job linked to my shift so that I understand my work responsibility. | • Job details accessible from shift screen | Employee | Medium | Planned
49 | UC-E08 | EMPLOYEE – DASHBOARD & SHIFTS | View Job Role | As an employee I want to see my job role so that I know what task I am responsible for. | • Job role displayed on shift / job detail screen | Employee | Medium | Planned
50 | UC-E09 | EMPLOYEE – DASHBOARD & SHIFTS | View Site Location | As an employee I want to view the work site location so that I can travel to the correct place. | • Map opens with site pin • Directions available | Employee | Medium | Planned
51 | UC-E10 | EMPLOYEE – DASHBOARD & SHIFTS | View Shift Progress | As an employee I want to see shift progress status (pending / active / completed). | • Status badge visible on shift card | Employee | Medium | Planned
52 | UC-E11 | EMPLOYEE – DASHBOARD & SHIFTS | Complete Shift | As an employee I want to mark my shift as completed so that the system shows the work as finished. | • Complete button available after clock-out • Status updated | Employee | Medium | Planned
EMPLOYEE – ATTENDANCE
53 | UC-E12 | EMPLOYEE – ATTENDANCE | Clock In | As an employee I want to clock in when I start work so that my attendance is recorded. | • Clock-in button visible at shift start • Time saved correctly | Employee | High | Planned
54 | UC-E13 | EMPLOYEE – ATTENDANCE | Clock In with Location | As an employee I want my location to be captured during clock-in so that the company can verify I am at the correct site. | • GPS coordinates captured and sent to backend | Employee | High | Planned
55 | UC-E14 | EMPLOYEE – ATTENDANCE | Clock In with Photo | As an employee I want to upload a photo during clock-in so that attendance can be verified visually. | • Camera / gallery picker opens • Photo uploaded via multipart API | Employee | High | Planned
56 | UC-E15 | EMPLOYEE – ATTENDANCE | Start Break | As an employee I want to start my break so that break time is tracked. | • Break start button functional • Break start time saved | Employee | High | Planned
57 | UC-E16 | EMPLOYEE – ATTENDANCE | End Break | As an employee I want to end my break so that my active working time continues. | • Break end button functional • Break duration calculated | Employee | High | Planned
58 | UC-E17 | EMPLOYEE – ATTENDANCE | Clock Out | As an employee I want to clock out when my work ends so that my shift completion time is recorded. | • Clock-out time saved • Manager notified | Employee | High | Planned
59 | UC-E18 | EMPLOYEE – ATTENDANCE | Clock Out with Photo | As an employee I want to upload a photo during clock-out so that my manager can verify shift completion. | • Photo captured and uploaded • Linked to attendance record | Employee | Medium | Planned
60 | UC-E19 | EMPLOYEE – ATTENDANCE | Clock Out with Reason (Early) | As an employee I want to add a reason when clocking out early so that the manager knows why I ended my shift early. | • Reason field mandatory for early clock-out • Reason sent to backend | Employee | High | Planned
61 | UC-E20 | EMPLOYEE – ATTENDANCE | Emergency Clock Out | As an employee I want to emergency clock out so that I can leave a shift safely in urgent situations. | • Emergency clock-out button available • Manager receives emergency notification | Employee | High | Planned
62 | UC-E21 | EMPLOYEE – ATTENDANCE | Send Emergency Notification | As an employee I want to send an emergency alert so that my manager is informed quickly. | • Emergency alert sent to manager immediately | Employee | High | Planned
EMPLOYEE – LEAVE
63 | UC-E22 | EMPLOYEE – LEAVE | View Leave Balance | As an employee I want to view my leave balance so that I know how many leave days I have. | • Balance shown on leave screen | Employee | Medium | Planned
64 | UC-E23 | EMPLOYEE – LEAVE | Create Leave Request | As an employee I want to submit a leave request so that I can ask for time off. | • Leave dates selected • Request submitted • Manager notified | Employee | High | Planned
65 | UC-E24 | EMPLOYEE – LEAVE | View My Leave Requests | As an employee I want to view my submitted leave requests so that I can track their progress. | • Leave list with status (pending/approved/rejected/cancelled) displayed | Employee | High | Planned
66 | UC-E25 | EMPLOYEE – LEAVE | Cancel Leave Request | As an employee I want to cancel a leave request so that I can remove a request I no longer need. | • Cancel option on pending requests • Request removed from active list | Employee | Medium | Planned
67 | UC-E26 | EMPLOYEE – LEAVE | Receive Leave Approval Notification | As an employee I want to receive a notification when my leave is approved so that I know I can take leave. | • Push notification sent on approval | Employee | High | Planned
68 | UC-E27 | EMPLOYEE – LEAVE | Receive Leave Rejection Notification | As an employee I want to receive a notification when my leave is rejected so that I can adjust my plans. | • Push notification sent on rejection | Employee | High | Planned
EMPLOYEE – DOCUMENTS & CERTIFICATES
69 | UC-E28 | EMPLOYEE – DOCUMENTS & CERTIFICATES | View Certificates | As an employee I want to view my certificates so that I know what qualification documents are saved. | • Certificate list fetched and displayed | Employee | Medium | Planned
70 | UC-E29 | EMPLOYEE – DOCUMENTS & CERTIFICATES | Upload Certificate | As an employee I want to upload a certificate so that my qualifications can be verified. | • File picker opens • Certificate saved to backend | Employee | High | Planned
71 | UC-E30 | EMPLOYEE – DOCUMENTS & CERTIFICATES | Update Certificate | As an employee I want to replace or update a certificate so that expired documents can be corrected. | • Update flow available • New file replaces old | Employee | Medium | Planned
72 | UC-E31 | EMPLOYEE – DOCUMENTS & CERTIFICATES | Delete Certificate | As an employee I want to delete an old certificate so that incorrect documents are removed. | • Delete confirmation shown • Certificate removed | Employee | Medium | Planned
73 | UC-E32 | EMPLOYEE – DOCUMENTS & CERTIFICATES | View Uploaded Document | As an employee I want to open a document so that I can check what I submitted. | • Document opens in media viewer | Employee | Low | Planned
EMPLOYEE – ONBOARDING
74 | UC-E33 | EMPLOYEE – ONBOARDING | Complete Onboarding | As a new employee I want to complete onboarding so that I can become an active employee. | • Multi-step onboarding screens present • Submission accepted by API | Employee | High | Planned
75 | UC-E34 | EMPLOYEE – ONBOARDING | Fetch Invitation by Email | As a new employee I want the app to find my invitation using my email so that I can begin onboarding. | • Invitation fetched by email • Pre-filled where possible | Employee | High | Planned
76 | UC-E35 | EMPLOYEE – ONBOARDING | Submit Personal Information | As a new employee I want to submit my personal details so that my employee profile can be created. | • Name, contact, address fields submitted successfully | Employee | High | Planned
77 | UC-E36 | EMPLOYEE – ONBOARDING | Submit Bank Details | As a new employee I want to submit bank details so that salary/payment information can be stored. | • Bank detail fields available • Data saved correctly | Employee | High | Planned
78 | UC-E37 | EMPLOYEE – ONBOARDING | Lookup Bank Using BSB | As a new employee I want the app to look up my bank using BSB so that I know the bank details are correct. | • BSB entered → bank name auto-filled | Employee | Medium | Planned
79 | UC-E38 | EMPLOYEE – ONBOARDING | Upload Identity Documents | As a new employee I want to upload identity documents so that my onboarding can be verified. | • ID document upload present • Multipart submission works | Employee | High | Planned
80 | UC-E39 | EMPLOYEE – ONBOARDING | Resubmit Rejected Onboarding Data | As an employee I want to resubmit rejected information so that my onboarding can be approved. | • Rejected fields highlighted • Resubmission accepted by API | Employee | High | Planned
81 | UC-E40 | EMPLOYEE – ONBOARDING | Submit Profile Photo During Onboarding | As a new employee I want to upload a profile photo during onboarding so that my employee profile is complete. | • Image picker available during onboarding • Photo uploaded successfully | Employee | High | Planned
EMPLOYEE – EMERGENCY & CONTACTS
82 | UC-E41 | EMPLOYEE – EMERGENCY & CONTACTS | Add Emergency Contact | As an employee I want to add emergency contact details so that the company can contact someone if needed. | • Emergency contact form saves correctly | Employee | Medium | Planned
83 | UC-E42 | EMPLOYEE – EMERGENCY & CONTACTS | Update Emergency Contact | As an employee I want to update emergency contact details so that the information remains current. | • Existing contact fields editable and saved | Employee | Medium | Planned
84 | UC-E43 | EMPLOYEE – EMERGENCY & CONTACTS | Call Emergency Contact | As an employee I want to call an emergency contact from the app so that I can quickly get help. | • Phone link opens device dialler | Employee | Medium | Planned
MANAGER – DASHBOARD & COMPANY
85 | UC-M01 | MANAGER – DASHBOARD & COMPANY | View Manager Dashboard | As a manager/admin I want to view a dashboard so that I can monitor workforce activity. | • Summary of projects, jobs, shifts, employees shown • Quick-action navigation available | Manager / Admin | High | Planned
86 | UC-M02 | MANAGER – DASHBOARD & COMPANY | View Companies | As a manager/admin I want to view companies so that I can manage business entities. | • Company list displayed | Manager / Admin | Medium | Planned
87 | UC-M03 | MANAGER – DASHBOARD & COMPANY | Create Company | As a manager/admin I want to create a company so that projects can be linked to the correct organization. | • Company name and details saved • Company visible in list | Manager / Admin | High | Planned
88 | UC-M04 | MANAGER – DASHBOARD & COMPANY | Edit Company | As a manager/admin I want to edit company details so that company information remains correct. | • Existing fields editable • Update saved | Manager / Admin | Medium | Planned
89 | UC-M05 | MANAGER – DASHBOARD & COMPANY | Delete Company | As a manager/admin I want to delete a company so that unused company records are removed. | • Confirmation prompt shown • Company removed | Manager / Admin | Low | Planned
MANAGER – SITES
90 | UC-M06 | MANAGER – SITES | View Sites | As a manager/admin I want to view work sites so that I can manage physical locations. | • All sites listed | Manager / Admin | Medium | Planned
91 | UC-M07 | MANAGER – SITES | Create Site | As a manager/admin I want to create a site so that work can be assigned to a location. | • Site name, address, GPS saved • Linked to project | Manager / Admin | High | Planned
92 | UC-M08 | MANAGER – SITES | Edit Site | As a manager/admin I want to update site details so that employees go to the correct place. | • Fields editable and saved | Manager / Admin | Medium | Planned
93 | UC-M09 | MANAGER – SITES | Delete Site | As a manager/admin I want to delete unused sites so that old locations are removed. | • Confirmation shown • Site removed | Manager / Admin | Low | Planned
94 | UC-M10 | MANAGER – SITES | View Employees Assigned to Site | As a manager/admin I want to see employees assigned to a site so that I know who is working there. | • Employee list filtered by site | Manager / Admin | Medium | Planned
MANAGER – PROJECTS
95 | UC-M11 | MANAGER – PROJECTS | View Projects | As a manager/admin I want to view all projects so that I can manage company work. | • Project list displayed | Manager / Admin | High | Planned
96 | UC-M12 | MANAGER – PROJECTS | Create Project | As a manager/admin I want to create a project so that work can be grouped properly. | • Project name, company, site, details saved | Manager / Admin | High | Planned
97 | UC-M13 | MANAGER – PROJECTS | Create Project in Steps | As a manager/admin I want project creation to be step-by-step so that entering project details is easier. | • Multi-step creation screens present | Manager / Admin | Medium | Planned
98 | UC-M14 | MANAGER – PROJECTS | Edit Project | As a manager/admin I want to update project details so that project information stays accurate. | • Fields editable and saved | Manager / Admin | Medium | Planned
99 | UC-M15 | MANAGER – PROJECTS | View Project Details | As a manager/admin I want to open a project so that I can see related jobs and sites. | • Jobs and sites visible under project | Manager / Admin | High | Planned
100 | UC-M16 | MANAGER – PROJECTS | Delete Project | As a manager/admin I want to delete unused projects so that old records do not clutter the system. | • Confirmation shown • Project removed | Manager / Admin | Low | Planned
MANAGER – JOBS
101 | UC-M17 | MANAGER – JOBS | View Jobs | As a manager/admin I want to view jobs so that I can track active and completed work. | • All jobs listed with status | Manager / Admin | High | Planned
102 | UC-M18 | MANAGER – JOBS | Create Job | As a manager/admin I want to create a job so that work can be assigned to employees. | • Job details saved • Job visible in list | Manager / Admin | High | Planned
103 | UC-M19 | MANAGER – JOBS | Create Job with Image | As a manager/admin I want to upload an image for a job so that employees can better understand the job. | • Image uploaded via multipart API • Visible on job detail screen | Manager / Admin | High | Planned
104 | UC-M20 | MANAGER – JOBS | Edit Job | As a manager/admin I want to edit job details so that job information stays current. | • Job name, description, image, role editable and saved | Manager / Admin | Medium | Planned
105 | UC-M21 | MANAGER – JOBS | Complete Job | As a manager/admin I want to mark a job as complete so that finished work is separated from active work. | • Complete action available • Status updated | Manager / Admin | Medium | Planned
106 | UC-M22 | MANAGER – JOBS | Delete Job | As a manager/admin I want to delete a job so that cancelled or incorrect jobs are removed. | • Confirmation shown • Job removed | Manager / Admin | Low | Planned
107 | UC-M23 | MANAGER – JOBS | Create Job Role Type | As a manager/admin I want to create job role types so that employee responsibilities are clear. | • Role type saved and available when creating shifts | Manager / Admin | Medium | Planned
108 | UC-M24 | MANAGER – JOBS | Delete Job Role Type | As a manager/admin I want to delete unused job role types so that role lists stay clean. | • Role type removed | Manager / Admin | Low | Planned
109 | UC-M25 | MANAGER – JOBS | View Assigned Employees for Job | As a manager/admin I want to see employees assigned to a job. | • Employee list filtered by job | Manager / Admin | Medium | Planned
MANAGER – SHIFTS
110 | UC-M26 | MANAGER – SHIFTS | View Shifts | As a manager/admin I want to view all shifts so that I can monitor schedules. | • All shifts listed with status | Manager / Admin | High | Planned
111 | UC-M27 | MANAGER – SHIFTS | Create Shift | As a manager/admin I want to create a shift so that employees know when they need to work. | • Shift date, time, job, site, employee saved • Visible to assigned employee | Manager / Admin | High | Planned
112 | UC-M28 | MANAGER – SHIFTS | Assign Employee to Shift | As a manager/admin I want to assign an employee to a shift so that each shift has responsible workers. | • Employee selectable during shift creation | Manager / Admin | High | Planned
113 | UC-M29 | MANAGER – SHIFTS | Edit Shift | As a manager/admin I want to update shift information so that schedule changes are reflected. | • Date, time, employee, job fields editable and saved | Manager / Admin | High | Planned
114 | UC-M30 | MANAGER – SHIFTS | Delete Shift | As a manager/admin I want to delete a shift so that cancelled shifts are removed. | • Confirmation shown • Shift removed | Manager / Admin | Medium | Planned
115 | UC-M31 | MANAGER – SHIFTS | Notify Employee About Shift | As a manager/admin I want the employee to receive a shift notification so that they know they have been assigned. | • Push notification sent on shift assignment | Manager / Admin | High | Planned
116 | UC-M32 | MANAGER – SHIFTS | View Shift Progress | As a manager/admin I want to view shift progress so that I know if shifts are pending, active, or completed. | • Status shown on shift list | Manager / Admin | Medium | Planned
117 | UC-M33 | MANAGER – SHIFTS | View Completed Shifts | As a manager/admin I want to view completed shifts so that I can confirm finished work. | • Completed shifts filterable on shift list | Manager / Admin | Medium | Planned
MANAGER – EMPLOYEES
118 | UC-M34 | MANAGER – EMPLOYEES | View Employees | As a manager/admin I want to view all employees so that I can manage the workforce. | • Employee list displayed with basic info | Manager / Admin | High | Planned
119 | UC-M35 | MANAGER – EMPLOYEES | Search Employee | As a manager/admin I want to search employees so that I can quickly find a specific person. | • Search filters employee list by name | Manager / Admin | Medium | Planned
120 | UC-M36 | MANAGER – EMPLOYEES | View Employee Details | As a manager/admin I want to open employee details so that I can review employee information. | • Profile, documents, shifts visible | Manager / Admin | High | Planned
121 | UC-M37 | MANAGER – EMPLOYEES | View Employee Certificates | As a manager/admin I want to view employee certificates so that I can confirm qualifications. | • Certificate list fetched for employee | Manager / Admin | Medium | Planned
122 | UC-M38 | MANAGER – EMPLOYEES | View Employee Documents | As a manager/admin I want to view employee documents so that I can check compliance records. | • Document list visible | Manager / Admin | High | Planned
123 | UC-M39 | MANAGER – EMPLOYEES | Approve Employee Document | As a manager/admin I want to approve valid employee documents so that employee records are accepted. | • Approve action saved • Employee notified | Manager / Admin | High | Planned
124 | UC-M40 | MANAGER – EMPLOYEES | Reject Employee Document | As a manager/admin I want to reject incorrect documents so that employees can resubmit valid files. | • Reject action saved with reason • Employee notified | Manager / Admin | High | Planned
125 | UC-M41 | MANAGER – EMPLOYEES | View Employee Next of Kin | As a manager/admin I want to view employee next-of-kin details so that emergency contacts are available. | • Next-of-kin screen accessible from employee profile | Manager / Admin | Medium | Planned
MANAGER – LEAVE
126 | UC-M42 | MANAGER – LEAVE | View Leave Requests | As a manager/admin I want to view all leave requests so that I can manage employee availability. | • All requests listed with status | Manager / Admin | High | Planned
127 | UC-M43 | MANAGER – LEAVE | Approve Leave Request | As a manager/admin I want to approve a leave request so that the employee can take time off. | • Approve action saved • Leave status updated to approved | Manager / Admin | High | Planned
128 | UC-M44 | MANAGER – LEAVE | Reject Leave Request | As a manager/admin I want to reject a leave request so that unavailable leave is clearly handled. | • Reject action saved • Employee receives rejection notification | Manager / Admin | High | Planned
129 | UC-M45 | MANAGER – LEAVE | Notify Employee of Leave Decision | As a manager/admin I want the employee to receive leave decision notifications so that they know the result quickly. | • Push notification sent on approve or reject | Manager / Admin | High | Planned
130 | UC-M46 | MANAGER – LEAVE | View Pending Requests | As a manager/admin I want to view pending employee requests so that I can respond efficiently. | • Pending requests screen shows all outstanding items | Manager / Admin | High | Planned
MANAGER – ATTENDANCE
131 | UC-M47 | MANAGER – ATTENDANCE | View Attendance Records | As a manager/admin I want to view attendance records so that I can check employee work time. | • Clock-in, clock-out, breaks, and status shown | Manager / Admin | High | Planned
132 | UC-M48 | MANAGER – ATTENDANCE | View Clock-In Photo | As a manager/admin I want to view the clock-in photo so that I can verify the employee started correctly. | • Photo URL fetched and displayed | Manager / Admin | Medium | Planned
133 | UC-M49 | MANAGER – ATTENDANCE | View Clock-Out Photo | As a manager/admin I want to view the clock-out photo so that I can verify the employee completed the shift. | • Photo URL fetched and displayed | Manager / Admin | Medium | Planned
134 | UC-M50 | MANAGER – ATTENDANCE | View Early Clock-Out Reasons | As a manager/admin I want to view reasons for early clock-out to understand employee issues. | • Reason shown with employee and time details | Manager / Admin | Medium | Planned
135 | UC-M51 | MANAGER – ATTENDANCE | Approve Attendance | As a manager/admin I want to approve attendance so that valid work records are accepted. | • Approve action with optional note saved | Manager / Admin | High | Planned
136 | UC-M52 | MANAGER – ATTENDANCE | Reject Attendance | As a manager/admin I want to reject incorrect attendance so that false records are not accepted. | • Reject action with note saved | Manager / Admin | High | Planned
137 | UC-M53 | MANAGER – ATTENDANCE | Add Attendance Approval Note | As a manager/admin I want to add a note when approving or rejecting attendance so that the decision is documented. | • Note field available and saved with decision | Manager / Admin | Medium | Planned
MANAGER – REPORTS
138 | UC-M54 | MANAGER – REPORTS | View Attendance Report | As a manager/admin I want to generate attendance reports so that I can analyze employee attendance. | • Report fetched and displayed • Filterable by date/employee | Manager / Admin | High | Planned
139 | UC-M55 | MANAGER – REPORTS | View Employee Performance Report | As a manager/admin I want to generate employee performance reports so that I can evaluate worker performance. | • Overall performance report generated | Manager / Admin | Medium | Planned
140 | UC-M56 | MANAGER – REPORTS | View Weekly Report | As a manager/admin I want to generate weekly employee reports so that I can review performance by week. | • Weekly report generated with date filter | Manager / Admin | Medium | Planned
141 | UC-M57 | MANAGER – REPORTS | View Date Range Report | As a manager/admin I want to generate a report for a custom date range so that I can analyze a specific period. | • Date range picker available • Report generated for selected period | Manager / Admin | Medium | Planned
142 | UC-M58 | MANAGER – REPORTS | Open Reports Section | As a manager/admin I want to open reports from the menu so that I can access performance and attendance insights. | • Reports section accessible from manager side nav | Manager / Admin | Medium | Planned
MANAGER – LOCATION & ORG
143 | UC-M59 | MANAGER – LOCATION & ORG | Track Employee Location | As a manager/admin I want to track employee locations so that I can confirm employees are at the correct site. | • Employee locations displayed on map | Manager / Admin | High | Planned
144 | UC-M60 | MANAGER – LOCATION & ORG | Select Site for Location Tracking | As a manager/admin I want to select a site before tracking so that I only view employees from that location. | • Site picker shown before opening map tracking | Manager / Admin | High | Planned
145 | UC-M61 | MANAGER – LOCATION & ORG | Switch Organization | As a manager/admin I want to switch organization/tenant so that I can manage the correct company. | • Organization picker accessible from navbar • Switch confirmed | Manager / Admin | High | Planned
146 | UC-M62 | MANAGER – LOCATION & ORG | View Selected Organization | As a manager/admin I want to see which organization is selected so that I avoid managing the wrong tenant. | • Org name shown in dashboard header | Manager / Admin | Medium | Planned
147 | UC-M63 | MANAGER – LOCATION & ORG | View Feature Availability | As a manager/admin I want to know which features are available for my organization. | • Feature gate blocks disabled features • Premium gate shown when feature is premium | Manager / Admin | Medium | Planned
ADMIN / SUPER ADMIN – TENANT MANAGEMENT
148 | UC-S01 | ADMIN / SUPER ADMIN – TENANT MANAGEMENT | Manage Tenant Features | As an admin I want to enable or disable tenant features so that organizations only use allowed modules. | • Feature toggle saved per tenant • FeatureGate enforced in UI | Admin / Super Admin | High | Planned
149 | UC-S02 | ADMIN / SUPER ADMIN – TENANT MANAGEMENT | Create Tenant | As an admin I want to create a tenant so that a new organization can use the application. | • Tenant details saved • Tenant active on creation | Admin / Super Admin | High | Planned
150 | UC-S03 | ADMIN / SUPER ADMIN – TENANT MANAGEMENT | Deactivate Tenant | As an admin I want to deactivate a tenant so that an organization's access can be paused. | • Tenant status set to inactive | Admin / Super Admin | High | Planned
151 | UC-S04 | ADMIN / SUPER ADMIN – TENANT MANAGEMENT | Reactivate Tenant | As an admin I want to reactivate a tenant so that the organization can use the app again. | • Tenant status set to active | Admin / Super Admin | Medium | Planned
152 | UC-S05 | ADMIN / SUPER ADMIN – TENANT MANAGEMENT | Soft Delete Tenant | As an admin I want to soft delete a tenant so that it can be removed without permanent loss. | • Tenant marked deleted • Not visible in active list | Admin / Super Admin | Medium | Planned
153 | UC-S06 | ADMIN / SUPER ADMIN – TENANT MANAGEMENT | Restore Tenant | As an admin I want to restore a deleted tenant so that accidental deletion can be fixed. | • Tenant restored and visible again | Admin / Super Admin | Medium | Planned
154 | UC-S07 | ADMIN / SUPER ADMIN – TENANT MANAGEMENT | View Recently Deleted Tenants | As an admin I want to view recently deleted tenants so that I can decide whether to restore them. | • Deleted tenant list available | Admin / Super Admin | Medium | Planned
ADMIN / SUPER ADMIN – ANNOUNCEMENTS
155 | UC-S08 | ADMIN / SUPER ADMIN – ANNOUNCEMENTS | Create Announcement | As an admin I want to create announcements so that users receive important information. | • Announcement created and active | Admin / Super Admin | Medium | Planned
156 | UC-S09 | ADMIN / SUPER ADMIN – ANNOUNCEMENTS | View Active Announcements | As an admin/user I want to view active announcements so that I know current important messages. | • Active announcements fetched by tenant | Employee / Manager / Admin | Medium | Planned
157 | UC-S10 | ADMIN / SUPER ADMIN – ANNOUNCEMENTS | View Announcement History | As an admin I want to view announcement history so that I can review previous messages. | • History screen shows past announcements | Admin / Super Admin | Low | Planned
158 | UC-S11 | ADMIN / SUPER ADMIN – ANNOUNCEMENTS | Delete Announcement | As an admin I want to delete an announcement so that outdated information is removed. | • Announcement deleted and no longer shown | Admin / Super Admin | Low | Planned
ADMIN / SUPER ADMIN – USER MANAGEMENT
159 | UC-S12 | ADMIN / SUPER ADMIN – USER MANAGEMENT | Impersonate User | As an admin I want to impersonate a user so that I can troubleshoot their account issues. | • Impersonation session started • Session clearly indicated in UI | Admin / Super Admin | Medium | Planned
160 | UC-S13 | ADMIN / SUPER ADMIN – USER MANAGEMENT | Stop User Impersonation | As an admin I want to stop impersonating a user so that I return to my own admin account. | • Impersonation ended • Own account restored | Admin / Super Admin | Medium | Planned
161 | UC-S14 | ADMIN / SUPER ADMIN – USER MANAGEMENT | View All Tenants | As an admin I want to view all tenants so that I can manage all organizations. | • Tenant list fetched and displayed | Admin / Super Admin | High | Planned

## Summary
ShiftSmart – Use Case Count by Module
Module | # Use Cases
AUTHENTICATION | 11
PROFILE & SETTINGS | 6
NOTIFICATIONS | 9
CHAT | 5
FILES & MEDIA | 3
SYSTEM / UX | 7
EMPLOYEE – DASHBOARD & SHIFTS | 11
EMPLOYEE – ATTENDANCE | 10
EMPLOYEE – LEAVE | 6
EMPLOYEE – DOCUMENTS & CERTIFICATES | 5
EMPLOYEE – ONBOARDING | 8
EMPLOYEE – EMERGENCY & CONTACTS | 3
MANAGER – DASHBOARD & COMPANY | 5
MANAGER – SITES | 5
MANAGER – PROJECTS | 6
MANAGER – JOBS | 9
MANAGER – SHIFTS | 8
MANAGER – EMPLOYEES | 8
MANAGER – LEAVE | 5
MANAGER – ATTENDANCE | 7
MANAGER – REPORTS | 5
MANAGER – LOCATION & ORG | 5
ADMIN / SUPER ADMIN – TENANT MANAGEMENT | 7
ADMIN / SUPER ADMIN – ANNOUNCEMENTS | 4
ADMIN / SUPER ADMIN – USER MANAGEMENT | 3
TOTAL USE CASES | 161